## Slide 1: CS 703 Applied Data Science Project Weekly Status Report
Professor Nicholas Nardi
Spring 2026

## Slide 2: So, What is This Status About?...
In the “Real” World, EVERY Project is Reported on EVERY Week…
Management is Informed as to Whether the Project is On Schedule, On Budget, and If There Any Issues or Risks That Could Impact the Project in the Long or Short Term…
As This Class Wants to Simulate the “Real” World, You Need to Report on Your Project EVERY Week…

## Slide 3: Ok, So How Does This Work?…
EVERY Week, You Need to Submit a FORMAL STATUS REPORT Detailing the Overall Status of Your Project…
There Will Be Two Parts to Your Weekly Status :
  Formal Project Status…
    Provides Insight Into Activities Completed, Activities in Progress, and Activities to Be Started…
    Alerts Management (Me) of Any Issues or Concerns That Need to Be Addressed…
  Personal Reflection…
    This is Like a Diary…It is Your THOUGHTS and FEELINGS on the Project and the Class, and How You Think Things Are Going…
    It is NOT a Rehash of Activities You Are Performing…Please Make Sure You Are Clear on This…

## Slide 4: Let’s Take This a Slide at a Time…
The Following Slides Discuss What Should Be Included on Each Slide of Your Status…
At the End of Those Slides is a Complete Sample Status Report…
IF ANYTHING DOES NOT MAKE SENSE, MAKE SURE YOU ASK…

## Slide 5: Title Slide…
Contains :
  Name of the Project…
  Week Ending Date…
    Note : the Project Week Always Ends on a Friday…
  Your Name…
  Status Submit Date…This is Typically a Saturday…
    If You Submit Your Status Late, the Submit Date Should Reflect That…

## Slide 6: Education Analysis Status Report Week Ending May 8, 2026 Submitted by John Smith May 10, 2026
NAME OF PROJECT…
WEEK ENDING DATE – This is Always a Friday Date…
YOUR NAME
DATE STATUS WAS SUBMITTED…

## Slide 7: Agenda Slide…
Status Overview…
Items Completed This Week…
Items In Progress…
Items To Be Started…
Samples of Items Completed This Week…
Issues, Risks, Concerns…
Next Steps…
Personal Reflection…
THIS IS THE EXACT AGENDA YOU NEED TO USE…
YOUR AGENDA IS THE SAME EVERY WEEK…
YOU SHOULD SEE SOME CONTINUITY IN WHAT YOU WRITE EVERY WEEK…
The Agenda NEVER Changes…

## Slide 8: Status Overview – Part 1…
This Slide is a Snapshot of the Entire Project…
You Should Show Your Status as Being:
  GREEN - Project on Plan, Project on Budget, No Project Impacting Issues…
  YELLOW - Project Generally on Plan, Project Generally on Budget, Potential Issues Exist That Could Impact the Project…
  RED - Project is NOT on Plan, Project is NOT on Budget, Issues Exist That Are Impacting the Project…
NOTE : If Your Project is NOT Green, You Need to Include on This Slide a SHORT Description Explaining Why…Detailed Explanations Should Appear Later in the Status…

## Slide 9: Status Overview – Part 2…
Show MAJOR Items Completed (i.e., “Data Analysis Completed”)…
Do NOT Show the Detail Behind the Item Completed (i.e., “Uploaded Tables”, “Cleaned Keys”, etc.)…
You Can Also Clip a Snapshot of Your Project Plan to Show Your Progress…
Be Sure to Show Original/Revised/Actual Start/End Dates for All Major Milestones…
IMPORTANT NOTE: EVERY Task in This Status MUST Have an ORIGINAL/REVISE/ACTUAL Start and End Date…

## Slide 10: Status Overview…
Project Status is Green
Completed 1.0 Business Understanding
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 8, 2026, Revised End Date : N/A, Actual End Date : May 9, 2026
All Items on Plan and On Budget
No Major issues
NOTE: THIS IS A SAMPLE OF A STATUS THAT HAS NO ISSUES…

## Slide 11: Status Overview…
Project Status is Green
Completed 1.0 Business Understanding
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 8, 2026, Revised End Date : N/A, Actual End Date : May 9, 2026
All Items on Plan and On Budget
No Major issues
NOTE: THIS IS A SAMPLE OF A STATUS THAT HAS NO ISSUES…
Notice the Status Color…

## Slide 12: Status Overview…
Project Status is Green
Completed 1.0 Business Understanding
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 8, 2026, Revised End Date : N/A, Actual End Date : May 9, 2026
All Items on Plan and On Budget
No Major issues
NOTE: THIS IS A SAMPLE OF A STATUS THAT HAS NO ISSUES…
Notice the Status Color…
Note : This is a Major Task That Was COMPLETED This Week…

## Slide 13: Status Overview…
Project Status is Green
Completed 1.0 Business Understanding
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 8, 2026, Revised End Date : N/A, Actual End Date : May 9, 2026
All Items on Plan and On Budget
No Major issues
We Will Discuss Date Formats Shortly!...

## Slide 14: Status Overview…
Project Status is Yellow
1.0 Business Understanding in progress
  Original Start Date : April 28, 2026, Revised Start Date : N/A, Actual Start Date : April 28, 2026
  Original End Date : May 10, 2026, Revised End Date : N/A, Actual End Date : N/A
Did not understand section of 1.0 Business Understanding in the CRISP-DM documentation…met with Professor Nardi on May 5 to review…
Anticipate completing Scope Document by May 12
No other major issues
NOTE: THIS IS A SAMPLE OF A STATUS THAT HAS AN ISSUE…

## Slide 15: Status Overview…
Project Status is Yellow
1.0 Business Understanding in progress
  Original Start Date : April 28, 2026, Revised Start Date : N/A, Actual Start Date : April 28, 2026
  Original End Date : May 10, 2026, Revised End Date : N/A, Actual End Date : N/A
Did not understand section of 1.0 Business Understanding in the CRISP-DM documentation…met with Professor Nardi on May 5 to review…
Anticipate completing Scope Document by May 12
No other major issues
Notice the Status Color…
NOTE: THIS IS A SAMPLE OF A STATUS THAT HAS AN ISSUE…

## Slide 16: Status Overview…
Project Status is Yellow
1.0 Business Understanding in progress
  Original Start Date : April 28, 2026, Revised Start Date : N/A, Actual Start Date : April 28, 2026
  Original End Date : May 10, 2026, Revised End Date : N/A, Actual End Date : N/A
Did not understand section of 1.0 Business Understanding in the CRISP-DM documentation…met with Professor Nardi on May 5 to review…
Anticipate completing Scope Document by May 12
No other major issues
Notice the Status Color…
Note the Reason WHY the Task is Late…
NOTE: THIS IS A SAMPLE OF A STATUS THAT HAS AN ISSUE…

## Slide 17: Items Completed in Current Week…
  This Slide Should List Each Task That Was Completed IN THE CURRENT WEEK; That is, Since the PRIOR Status…It is NOT a Running List of Items Completed…
  Every Item Completed Should Have a SHORT Description (i.e., 1 or 2 Sentences) of What Was Completed…
  For Every Item Completed, You Must Show the Original/Revised/Actual Start Date and the Original/Revised/Actual End Date…
  Your Project May Not Have Something Due EVERY Week…If That is the Case, Simply Say “Per Plan, No Items Completed This Week” or Words to That Effect…
  Any Task Completed But Not Completed on Time Needs to Have an Explanation as to Why…

## Slide 18: Hmmm, So What If I Completed PART of a Task…
  For the Purposes of This Status, an “Item” is Considered to Be an ENTIRE Task on the Project Plan That Has a Defined Start and End Date…
  For Example…
    Your Project Plan Has a Task “2.0 Data Understanding” With a Start Date of September 8 and an End Date of September 22…
    At the End of the First Week, You Completed Part of the Task But Not All…
    This Would Be Considered an Item In Progress – NOT Completed…
    Tasks are Only Considered Completed When the ENTIRE TASK is Done…

## Slide 19: But Completing a Task Early is Good, Right?…
  Tasks Completed a Day or Two Early are Fine…
  Tasks Completed a Week or So Early are NOT Fine and ALSO Require an Explanation...
  There are TWO Main Reasons for This…
    First…
      An Organization Has Set Aside Money and Resource for Your Project Based on YOUR Estimates…
      If You are a Week or So Early, That Typically Means You are UNDER Budget…
      If a Project is Under Budget, an Organization can Reallocate Those Funds to a Project that is Over Budget, or to Initiate a New Project, or to Anything They Want…
    Second…
      Task Completion is Also a Measure of How Well YOU Understand and Estimate Projects…
      If ONE Task Takes Less Time Than You Said, What About All the Subsequent Tasks?...

## Slide 20: Items In Progress…
Your Project Should ALWAYS Have SOMETHING In Progress…
For This Slide :
  List EACH Task That is in Progress…
  Provide a Task Status (i.e., Green, Yellow, Red)…Again, Any Task That is Yellow or Red Needs to Have an Explanation as to Why and Some Mitigation Plan to Get Back on Plan…
  Percent Complete (i.e., Where You Stand With Each Task)…
  Original/Revised/Actual Start Date…Original/Revised End Date…
    NOTE: AS THE TASK IS "IN PROGRESS" THERE IS NO ACTUAL END DATE…
  Any Comments, Questions, Issues, Concerns Or Risks That You Have Regarding the Task…
NOTE: Your Project Plan Should Have Most of This Information…You May Include a Snapshot of Your Project Plan Here and Then Supplement What is Missing…

## Slide 21: Items To Be Started…
  Your Project Should ALWAYS Have SOMETHING Waiting To Start…
  You Should ALWAYS Have 2 or 3 Tasks Here…
  For This Slide :
  List EACH Major Task or Phase That is PLANNED To Be Started in the Next Week or Two, But Has Not Yet Been Started…
  Show Original/Revised Start/End Date…
  Any Comments, Questions, Issues, Concerns Or Risks That You Have Regarding That Task…
NOTE: Your Project Plan Should Have Most of This Information…You May Include a Snapshot of Your Project Plan Here and Then Supplement What is Missing…

## Slide 22: Okay, Wait…Time Out!...Why All This Stuff?!...
So, You Might Be Asking Yourself, “Why Do I Need to Show Those Three Items?”…
By Showing Tasks That Have Been Completed, Tasks That Are in Progress, and Tasks Coming Up, You Are Giving Management a “Three Week Spread” of What is Going on in the Project…
It Also Gives Managers That You Interact With an Opportunity to Express Concerns or Discuss Details If They Are Impacted by Those Items…
Think About School…You Know What Assignments You Have (or Should Have) Completed…You Know What Assignments You Are Working On and When You Think the Assignment Will Be Completed…and You Know What Assignments Are Coming Up So That You Can Begin to Panic…I Mean Begin to Plan…
Let’s Continue…

## Slide 23: As Long As We Are in a Time Out…Note On Dates…
I Keep Mentioning Original, Revised, and Actual Dates…
But What Exactly Are Each One…
  ORIGINAL START/END DATE : When You Create Your Approved Project Plan, Every Task is Given a Start Date and an End Date…These are the ORIGINAL Start and End Dates…These Dates NEVER Change…
  ACTUAL START/END DATE : Hopefully, Most Tasks Start on the Date We Planned and End on the Date We Planned…But That is Not Always the Case…Sometimes We Start or End a Task a Day or Two (or More) Earlier or Later…the Date That You ACTUALLY Start or End a Task is the ACTUAL Start and End Date…Only Started and/or Completed Tasks Have Actual Start/End Dates…
  REVISED START/END DATE : We Plan With All Good Intentions…Then Life Happens and We are Sometimes Forced to Make Major Revisions to Our Plan…In That Case, We Need to Create Revised Dates…Revised Dates Are RARELY Used…They are Not Intended to Correct Poor Planning…YOU CANNOT USE A REVISED DATE UNLESS YOU DISCUSS WITH ME AND GET MY APPROVAL…

## Slide 24: As Long As We Are in a Time Out…Note On Dates…
I Keep Mentioning Original, Revised, and Actual Dates…
But What Exactly Are Each One…
  ORIGINAL START/END DATE : When You Create Your Approved Project Plan, Every Task is Given a Start Date and an End Date…These are the ORIGINAL Start and End Dates…These Dates NEVER Change…
  ACTUAL START/END DATE : Hopefully, Most Tasks Start on the Date We Planned and End on the Date We Planned…But That is Not Always the Case…Sometimes We Start or End a Task a Day or Two (or More) Earlier or Later…the Date That You ACTUALLY Start or End a Task is the ACTUAL Start and End Date…Only Started and/or Completed Tasks Have Actual Start/End Dates…
  REVISED START/END DATE : We Plan With All Good Intentions…Then Life Happens and We are Sometimes Forced to Make Major Revisions to Our Plan…In That Case, We Need to Create Revised Dates…Revised Dates Are RARELY Used…They are Not Intended to Correct Poor Planning…YOU CANNOT USE A REVISED DATE UNLESS YOU DISCUSS WITH ME AND GET MY APPROVAL…
YOU MUST ALWAYS SHOW ORIGINAL, REVISED, AND ACTUAL DATES FOR EVERY TASKS…
IF THERE ARE NO REVISED OR ACTUAL DATES, YOU MUST STILL INCLUDE THEM – JUST PUT “N/A” AFTER THEM…

## Slide 25: Sample of Items In Progress…
The Purpose of This Slide is to Show a SAMPLE of Something Significant or Interesting That You Are Working On or Have Completed IN THE CURRENT WEEK…
You Can Show Either a Portion of the Item or the Entire Completed Item If the Item is Not Too Large…
You Should Also Have a SHORT Description of the What the Item is and WHY You Are Showing What You Are Showing…
For Example:
  If the Completed Task was a 20-Page 1.0 Business Understanding Document, Do NOT Show All 20-Pages…Maybe Show One or Two Sections…
  If the Completed Task Was the 3NF ERD, You Might Want to Show the Entire Completed Diagram…
  Any Links You Might Have to Any Item Would Also Go Here…MAKE SURE NO SPECIAL LOGIN IS REQUIRED!...

## Slide 26: Project Issues, Risks, Concerns…
  Every Project Has Issues, Risks and Concerns at Some Point…
  You Should List Issues, Risks, and Concerns SEPARATELY…
  For Each Issue, Risk, or Concern You Need to Identify the Impact and Some Mitigation Strategy…
  If You Have No Issues, Then Show “Issues: None”…the Same With Risks and Concerns…

## Slide 27: What’s the Difference?…
  Issues are REAL…They Have Already Occurred…They are Most ALWAYS Negative…
    Hardware will be delayed two weeks…
    Our budget has been cut 20%...
  Risks are POTENTIAL Problems…They MIGHT Occur in the Future…They Can Be Positive or Negative…
    NEGATIVE: The system feeding us data might be delayed two weeks…
    POSITIVE: Marketing now says that signup for the new system might be significantly higher than they expected…
  Concerns are Items That Are Out of Our Control That We Evaluate and Determine Could Be Impactful to Us…
    The current rate of inflation might cause the business to rethink this entire project…

## Slide 28: Notes on Issues, Risks, Concerns…
  These Items Relate to the PROJECT – NOT to the Business You Are Creating For…
    "A New Competitor is Entering the Market" is a BUSINESS issue – NOT a Project Issue…
  Items Put Here Are Issues, Risks and Concerns That Could Impact the ENTIRE Project…Task Issues Should Be On the Task Slides (Unless the TASK Issue Will Impact the PROJECT)…
    "Servers are Delayed Two Weeks" Will Impact the ENTIRE Project and SHOULD Be on This Slide…
    "Need to Add Four Junction Tables to the ERD" Will NOT Impact the Entire Project and Should NOT Be on This Slide…

## Slide 29: More Notes on Issues, Risks, Concerns…
  Anything Listed MUST be SPECIFIC to YOUR Project and They Must Be REAL…
    "Cannot Find a Significant Amount of Data" IS Real…
    “So Far the Only Data I Have Found is Over 5 Years Old" IS Real…
    “Internet Connect Might Go Down” is NOT Real…
    “I Might Get Sick” is NOT Real…
  It is Totally Fine to NOT Have Any Issues, Risks, or Concerns…

## Slide 30: Next Steps…
Your Project Should ALWAYS Have SOMETHING Coming Up!…
This Slide Will Should Include a Summary of the Items You Will Be Working On in the Coming Week(s)…
This Would Include :
  'Official' Items on Your Project Plan That You Are Continuing to Work On…
  'Official' Items on Your Project Plan That You Will Start in the Next Week or Two…
  Any Other Task or Research That Needs to Be Performed That is Not an 'Official' Task on Your Plan…
REMEMBER: EVERY Task Listed Should List the Original/Revised/Actual Start/End Dates…
NOTE: Your Project Plan Should Have Most of This Information…You May Include a Snapshot of Your Project Plan Here and Then Supplement What is Missing…

## Slide 31: Personal Reflection…
Many People Keep a Personal Journal When They Work on Projects, and Also, in Their Daily Lives (I Kept Project Journals for Decades!)…
Journaling and Reflecting Will Often Give You Real Insight Into Yourself and Increases Self Awareness…
It is Also a Big Stress Reliever – No Really!...
Each Week, I Want You to Create a Personal Reflection for This Project…
Your Reflection is NOT a Log of Activity…But Rather a Diary of Your THOUGHTS About How You Think You Are Doing…How You Think the Project is Doing…Any Concerns or Insights You Want to Share…
NO ONE WILL SEE THIS JOURNAL BUT ME…So Please Be As Candid As You Wish…
How Long Should the Journal Be?...If You Write 5 Slides You Have Written WAY Too Much…If You Have Written 2 Sentences You Have Written WAY Too Little…

## Slide 32: Notes on Your Status – Part 1…
YOU MUST USE POWER POINT…If You Have Some Reason for NOT Wanting to Use Power Point, You Need to Get My Approval…
Status Grade…
  Your Grade for This Status is Based on What You Write in the Status…NOT On What You Did or Did Not Do on the Project…
  For Example, If Your Tasks Were Late in a Given Week (Let’s Just Pretend!), But You Wrote a Good Status, You Could Still Get a Good Grade for Your Status…
Late Status…
  REMEMBER…This is a WEEKLY Status…
  It Makes No Sense for You to Submit a Status On July 25 Telling Me What You Did On May 23…
  Any Status That is More Than ONE WEEK LATE Will Be Given a ZERO With NO Opportunity to Submit…

## Slide 33: Notes on Your Status – Part 2…
Each Week You Should Create a New, Complete Status…
The NEW Status Should Be Added to the FRONT of All Previous Status Reports…
By the End of the Semester, You Should Have ONE Power Point With 14 Weeks of Status…
For Example:
  Week Ending May 9 :
    Create Your First Weekly Status…Let's Say Your Status is 10 Slides…
    Turn in Your Status Power Point With One Weeks Worth of Status and 10 Slides…
  Week Ending May 16 :
    Create Your Second Weekly Status…Let's Say Your Status is 10 Slides…
    The Slides for Your Second Weekly Status, Should Go on TOP of the Slides for Your First Weekly Status…
    Turn in Your Status Power Point With TWO Weeks Worth of Status and 20 Slides (i.e., May 9 AND May 16)…
  Do the Same Thing Ever Week…
  By the End of the Semester, You Will Turn in Your Status Power Point With 14 Weeks of Status and 140 Slides…

## Slide 34: Questions?…
If You Have ANY Questions About What I Am Looking for in Your Weekly Status, Please Reach Out to Me Via Messages in Blackboard…

## Slide 35: Sample Status…
The Remainder of the Power Point Shows a Complete Sample Status…
It is EXACTLY What I Am Looking for in Terms of Format…
The Content is Merely a Sample So You Can Get a Feel for What I am Looking For – DO NOT COPY THE CONTENT…
Feel Free to "Copy/Paste" These Slides and Use Them as a Template…

## Slide 36
Education Analyzer Status Report Week Ending May 09, 2026 Submitted by John Smith May 10, 2026

## Slide 37: Agenda…
Status Overview…
Items Completed in Current Week…
Items In Progress…
Items To Be Started…
Samples of Items Completed This Week…
Issues, Risks, Concerns…
Next Steps…
Personal Reflection…

## Slide 38: Status Overview…
Project Status is Yellow
1.0 Business Understanding Not Completed
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 9, 2026, Revised End Date : N/A, Actual End Date : N/A
Did not understand section 1.0 Business Understanding in the CRISP-DM documentation.
Met with Professor Nardi on May 5 to review sections of 1.0 Business Understanding in the CRISP-DM documentation
Anticipate completing Scope Document by May 12
No other major issues

## Slide 39: Items Completed in Current Week…
Project Topic Approved
  Task is GREEN – task 100% complete
  Original Start Date: April 28, 2026; Revised Start Date: n/a; Actual Start Date: April 30, 2026
  Original End Date: May 02, 2026; Revised End Date: n/a; Actual End Date: May 02, 2026
  Approved topic is “Education Analyzer"

## Slide 40: Items In Progress…
1.0 Business Understand document not completed
  Task is Yellow – task 90% complete
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 9, 2026, Revised End Date : N/A, Actual End Date : N/A
  Needed clarification on several items in the 1.0 Business Understanding document
    Met with Professor Nardi on May 5
    Anticipate completing 1.0 Business Understanding on May 12
    Will be working weekend to complete so as not to impact other project deliverables

## Slide 41: Items In Progress…
1.0 Business Understand document not completed
  Task is Yellow – task 90% complete
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 9, 2026, Revised End Date : N/A, Actual End Date : N/A
  Needed clarification on several items in the 1.0 Business Understanding document
    Met with Professor Nardi on May 1
    Anticipate completing 1.0 Business Understanding on May 12
    Will be working weekend to complete so as not to impact other project deliverables
Notice, the Three Items in Bullets Describe WHY the Task is Yellow and What Our Mitigation Plan Is…

## Slide 42: Items In Progress…
1.0 Business Understand document not completed
  Task is Yellow – task 90% complete
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 9, 2026, Revised End Date : N/A, Actual End Date : N/A
  Needed clarification on several items in the 1.0 Business Understanding document
    Met with Professor Nardi on May 1
    Anticipate completing 1.0 Business Understanding on May 12
    Will be working weekend to complete so as not to impact other project deliverables
Notice, the Three Items in Bullets Describe WHY the Task is Yellow and What Our Mitigation Plan Is…
In This Case, These Items Would Also Appear in "Next Steps" and/or "Issues, Risks, Concerns"…

## Slide 43: Items In Progress…
1.0 Business Understand document not completed
  Task is Yellow – task 90% complete
  Original Start Date : May 4, 2026, Revised Start Date : N/A, Actual Start Date : May 4, 2026
  Original End Date : May 9, 2026, Revised End Date : N/A, Actual End Date : N/A
  Needed clarification on several items in the 1.0 Business Understanding document
    Met with Professor Nardi on May 1
    Anticipate completing 1.0 Business Understanding on May 12
    Will be working weekend to complete so as not to impact other project deliverables
Notice, the Three Items in Bullets Describe WHY the Task is Yellow and What Our Mitigation Plan Is…
In This Case, These Items Would Also Appear in "Next Steps" and/or "Issues, Risks, Concerns"…
Notice Also the Original END Date Did NOT Change…
This is NOT a Revised Date…
This Will Be a Late Task…

## Slide 44: Items to Be Started…
2.0 Data Understanding
  Original Start Date: May 11, 2026; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: May 24, 2026; Revised End Date: n/a; Actual End Date: n/a
3.0 Data Preparation
  Original Start Date: May 25, 2026; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: June 07, 2026; Revised End Date: n/a; Actual End Date: n/a

## Slide 45: Items to Be Started…
2.0 Data Understanding
  Original Start Date: May 11, 2026; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: May 24, 2026; Revised End Date: n/a; Actual End Date: n/a
3.0 Data Preparation
  Original Start Date: May 25, 2026; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: June 07, 2026; Revised End Date: n/a; Actual End Date: n/a
Note How You Always Show an Original, Revised, and Actual Date Even If You Have None…Here They Act as Placeholders…

## Slide 46: Sample of Items Completed This Week…
Project Overview section of 1.0 Business Understanding document
This is key to the development of the rest of the system
  The “Education Analyzer" project is intended to help school administrators understand the factors that go into student success in High School and below. It will take into account demographics, gender, family history, student history, and other factors in order to offer suggestions for improving student success. The project includes various visualizations to support this topic.

## Slide 47: Project Issues, Risks, Concerns…
Issues
  Had some problems understanding all items in the 1.0 Business Understanding document
  Held a meeting with Professor Nardi on May 5 to clarify concerns
  Anticipate being back on schedule by May 12
Risks
  None at this time
Concerns
  None at this time

## Slide 48: Next Steps…
Follow up with Professor Nardi to review and verify items in the 1.0 Business Understanding document (May 11)
Complete 1.0 Business Understanding
  Original Start Date : April 28, 2026, Revised Start Date : N/A, Actual Start Date : April 28, 2026
  Original End Date : May 10, 2026, Revised End Date : N/A, Actual End Date : N/A
Begin work on 2.0 Data Understanding
  Original Start Date: May 11, 2026; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: May 24, 2026; Revised End Date: n/a; Actual End Date: n/a
Begin work 3.0 Data Preparation
  Original Start Date: May 25, 2026; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: June 07, 2026; Revised End Date: n/a; Actual End Date: n/a

## Slide 49: Personal Reflection…
Still getting the hang of writing these status reports. But I love how many notes Professor Nardi gives me every week. They are really helping me. I hope this week there will be no issues in the status report.
After reviewing the Business Understanding document, I was amazed at how many items actually go into determining what will be contained in a project. But the more I thought about it, the more I realized just how much of an impact these items have on what will eventually be developed. I have never been involved in most of those items, so I am looking forward to learning first-hand how they work. And while I am concerned about having to work on so many items that I am unfamiliar with, I know I can always ask Professor Nardi for help, and together we will get this done.

## Slide 50: Thank You!...