## Slide 1
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending July 24, 2026 Submitted by Gordon Oboh July 26, 2026

## Slide 2: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 3: Status Overview
Project Status: GREEN
Task 6.3: Final Presentation
  Status: GREEN — 100% complete
  Original Start: 12 Jul 2026 | Revised: N/A | Actual Start: 11 Jul 2026
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: 26 Jul 2026
Task 6.3: Final Report
  Status: GREEN — 5% complete
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: 26 Jul 2026
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 4: Items Completed This Week
Task 6.3: Final Presentation
  Status: GREEN — 100% complete
  Original Start: 12 Jul 2026 | Revised: N/A | Actual Start: 11 Jul 2026
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: 26 Jul 2026
  Final Presentation deliverable completed and submitted.
  Slide deck covers all required sections per professor’s outline.

## Slide 5: Items In Progress
Task 6.3: Final Report
  Status: GREEN — 5% complete
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: 26 Jul 2026
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A
  Initial work begun; outline and section headers drafted,
  building on all completed Phase 1–6 reports.

## Slide 6: Items To Be Started
Per plan, no new items to start this week.

## Slide 7: Sample of Items Completed This Week
What: Final Presentation — Title Slide
Why: Shows the completed presentation cover page; the full deliverable was submitted this week

## Slide 8: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  None at this time

## Slide 9: Next Steps
Task 6.3: Final Report (continue)
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: 26 Jul 2026
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 10: Personal Reflection
This is it — the final status report. Submitting the Final Presentation this week felt like crossing a major milestone. Seeing the full slide deck come together with all the required sections made me realize how much ground this project has covered, from the initial business problem to a working Random Forest model and a live demonstration. The presentation forced me to distill everything into a clear narrative, which was challenging but rewarding. I am starting the Final Report now, and while there is still work ahead, I feel confident because all the pieces are already written across the Phase 1–6 deliverables. It is mostly a matter of assembling and polishing. This course has been intense, but I have learned a lot about applying data science to real estate problems and about managing a project from start to finish.

## Slide 11: Thank You!...

## Slide 12
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending July 17, 2026 Submitted by Gordon Oboh July 17, 2026

## Slide 13: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 14: Status Overview
Project Status: GREEN
Task 6.3: Final Presentation
  Status: GREEN — 50% complete
  Original Start: 12 Jul 2026 | Revised: N/A | Actual Start: 11 Jul 2026
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Report
  Status: GREEN — 0% complete
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 15: Items Completed This Week
Per plan, no items completed this week.
  However Task 6.3: Final Presentation is scheduled to be completed next week.

## Slide 16: Items In Progress
Task 6.3: Final Presentation
  Status: GREEN — 50% complete
  Original Start: 12 Jul 2026 | Revised: N/A | Actual Start: 11 Jul 2026
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
  Slide deck structure finalized; key sections drafted
  including project overview, methodology, modeling
  results, and conclusions.

## Slide 17: Items To Be Started
Task 6.3: Final Report
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 18: Sample of Items Completed This Week
Final Presentation — Slide Deck Outline and Narrative Structure
Slide Deck Outline (In Progress):
- Project Overview — Business problem, all business & data mining goals/objectives, background material
- Summary of Each Phase — Key components of each phase as they relate to project goals (no task definitions, no full deliverable details)
- Data Cleansing — How and why data was cleansed and standardized (may combine with parts 4 & 5)
- Phase 4.0 — Modeling — All data visualizations meeting business goals, actual models with explanation, insight provided, potential business impact (may combine with parts 3 & 5)
- LIVE Demonstration — Video showing code execution and working models that coincide with models shown above (may combine with parts 3 & 4)
- Lessons Learned — Technology, Management, and Personal lessons learned
- Conclusion — Did the project meet Business and Data Mining goals? Why or why not? Final thoughts

## Slide 19: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  None at this time

## Slide 20: Next Steps
Task 6.3: Final Presentation (continue)
  Original Start: 12 Jul 2026 | Revised: N/A | Actual Start: 11 Jul 2026
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Report
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 21: Personal Reflection
With Phase 6 submitted and the finish line in sight, this week felt more structured than the last. Getting the presentation to 50% gave me a clear picture of what remains, and the slide outline is starting to tell the full story of the project from start to finish. The Random Forest results are strong enough that I feel confident presenting them. The biggest remaining task is translating all the technical detail into something concise and visually clear for the audience. I have resisted starting the Final Report early because I want to focus on one deliverable at a time and do it well. Next week will be about polishing the slides and rehearsing the flow.

## Slide 22: Thank You!...

## Slide 23
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending July 10, 2026 Submitted by Gordon Oboh July 11, 2026

## Slide 24: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 25: Status Overview
Project Status: GREEN
Task 6.1: Plan Deployment
  Status: GREEN — 100% complete
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 11 Jul 2026 | Revised: N/A | Actual End: 10 Jul 2026
Task 6.2: Plan Monitoring and Maintenance
  Status: GREEN — 100% complete
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 11 Jul 2026 | Revised: N/A | Actual End: 10 Jul 2026
Task 6.3: Final Presentation
  Status: GREEN — 3% complete
  Original Start: 12 Jul 2026 | Revised: N/A | Actual Start: 11 Jul 2026
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Report
  Status: GREEN — 0% complete
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 26: Items Completed This Week
Task 6.1: Plan Deployment
  Status: GREEN — 100% complete
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 11 Jul 2026 | Revised: N/A | Actual End: 10 Jul 2026
  Deployment Plan completed: model packaging, REST API
  architecture, documentation, training and support.
Task 6.2: Plan Monitoring and Maintenance
  Status: GREEN — 100% complete
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 11 Jul 2026 | Revised: N/A | Actual End: 10 Jul 2026
  Monitoring and Maintenance Plan completed: performance
  monitoring, data drift detection, retraining schedule,
  version control, and maintenance responsibilities.

## Slide 27: Items In Progress
Task 6.3: Final Presentation
  Status: GREEN — 3% complete
  Original Start: 12 Jul 2026 | Revised: N/A | Actual Start: 11 Jul 2026
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
  Preliminary planning started; slide deck structure being
  outlined.

## Slide 28: Items To Be Started
Task 6.3: Final Report
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 29: Sample of Items Completed This Week
Phase 6 Report — Deployment and Monitoring Plans
6.1 Plan Deployment:
  Model Packaging: serialised RF pipeline via joblib
  Architecture: Flask/FastAPI REST API, Docker, cloud
  Documentation: technical guide, user guide, data dict.
  Training: stakeholder orientation, single contact point
6.2 Plan Monitoring and Maintenance:
  Performance: MAE ($35.58), R² (0.946), drift tracking
  Data Drift: monthly K-S tests, chi-square on categories
  Retraining: quarterly + triggers (MAE +20%, drift, events)
  Versioning: rf_model_v2_2026-10-01.joblib naming, git
  Maintenance: single data scientist, scalable team

## Slide 30: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  None at this time

## Slide 31: Next Steps
Task 6.3: Final Presentation (continue)
  Original Start: 12 Jul 2026 | Revised: N/A | Actual Start: 11 Jul 2026
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Report
  Original Start: 25 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 32: Personal Reflection
Phase 6 is now complete, and looking back, I have to be honest, I fell into a mental loop last week trying to figure out the schedule and lost track of how the task dates actually map to the assignment deadlines. I was overthinking it, and it showed in my previous week of the status report where I tried to move Original dates around instead of just letting them be. That wasted time I could have spent actually working. Professor Nardi's feedback helped me reset: the Phase 6 report is due July 11. Writing the Deployment Plan and Monitoring Plan was useful in its own way. Since there's no real production deployment, it required thinking through a hypothetical scenario, which felt less natural than working with actual model results. But it helped me understand what a real deployment would need; model serialisation, API architecture, data drift detection, retraining schedules. Phase 6 is submitted, and now I can focus on the final deliverables without the schedule confusion hanging over my head.

## Slide 33: Thank You!...

## Slide 34
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending July 3, 2026 Submitted by Gordon Oboh July 4, 2026

## Slide 35: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 36: Status Overview
Project Status: GREEN
Task 5.2: Review Process
  Status: GREEN — 100% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: 4 Jul 2026
Task 5.3: Determine Next Steps
  Status: GREEN — 100% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 20 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: 4 Jul 2026
Task 6.1: Plan Deployment
  Status: GREEN — 7% complete
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.2: Plan Monitoring and Maintenance
  Status: GREEN — 7% complete
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A

## Slide 37: Items Completed This Week
Task 5.2: Review Process
  Status: GREEN — 100% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: 4 Jul 2026
  Process Evaluation Report completed
  Lessons learned: K-Means clustering impact, region-based IQR
Task 5.3: Determine Next Steps
  Status: GREEN — 100% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 20 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: 4 Jul 2026
  Deployment vs. revise decision documented
  Phase 5 report completed and submitted

## Slide 38: Items In Progress
Task 6.1: Plan Deployment
  Status: GREEN — 7% complete
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A
  Preliminary research started: deployment plan outline, model packaging
  Remaining: write full Deployment Plan section for Phase 6 report
Task 6.2: Plan Monitoring and Maintenance
  Status: GREEN — 7% complete
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A
  Preliminary research started: monitoring strategy outline
  Remaining: write full Monitoring and Maintenance Plan for Phase 6 report

## Slide 39: Items To Be Started
Task 6.3: Final Presentation
  Original Start: 19 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Report
  Original Start: 19 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 40: Sample of Items Completed This Week
Phase 5 Report — Evaluation Summary
Model Performance (5.1 Evaluate Results):
Top Features: location_cluster (1), region (2-3), sqfeet (2-3)
Process Review (5.2): Two key lessons — K-Means clustering around cities was the most impactful engineering decision; region-based IQR outlier handling outperformed national-level filtering.
Next Steps Decision (5.3): Recommendation is revise — six improvements proposed including K-Means optimization, larger datasets, NLP on description text, GPU acceleration, weighted ensemble, and additional feature engineering.
Metric | RF | XGB | HistGB
R² | 0.946 | 0.939 | 0.934
MAE | $35.58 | $46.47 | $47.07
RMSE | $77.32 | $82.58 | $85.70

## Slide 41: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  None at this time

## Slide 42: Next Steps
Task 6.1: Plan Deployment (continue)
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.2: Plan Monitoring and Maintenance (continue)
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: 4 Jul 2026
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Presentation
  Original Start: 19 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Report
  Original Start: 19 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 43: Personal Reflection
Phase 5 is now complete, and the Phase 5 PDF report was submitted this week. Looking back, the evaluation phase confirmed what the modeling metrics were already showing; Random Forest is the strongest model, and location drives price more than any individual amenity. The process review was valuable; I was surprised how much impact the K-Means clustering and region-based IQR had on the final results. Starting Phase 6 feels like the home stretch. I know the deployment plan and monitoring plan are academic exercises rather than a real production deployment, but Professor Nardi made it clear they still need to be thorough. The main milestones ahead are the final presentation and final report, and I want to make sure those get enough time in July.

## Slide 44: Thank You!...

## Slide 45
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending June 26, 2026 Submitted by Gordon Oboh June 26, 2026

## Slide 46: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 47: Status Overview
Project Status: GREEN
Task 5.1: Evaluate Results
  Status: GREEN — 100% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: 26 Jun 2026
Task 5.2: Review Process
  Status: GREEN — 60% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
Task 5.3: Determine Next Steps
  Status: GREEN — 20% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 20 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A

## Slide 48: Items Completed This Week
Task 5.1: Evaluate Results
  Status: GREEN — 100% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: 26 Jun 2026
  Model comparison: Random Forest selected as best performer (R²=0.946, MAE=$35.58)
  Business-goal alignment assessment completed
  Result Assessment and Model Approval deliverables documented

## Slide 49: Items In Progress
Task 5.2: Review Process
  Status: GREEN — 60% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
  Process review in progress: documenting what worked well, gaps, lessons learned
  Remaining: finalise Process Evaluation Report
Task 5.3: Determine Next Steps
  Status: GREEN — 20% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 20 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
  Preliminary next-step options identified
  Remaining: document possible actions (deploy vs. revise), final decision, Phase 5 report

## Slide 50: Items To Be Started
Task 6.1: Plan Deployment
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.2: Plan Monitoring and Maintenance
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A

## Slide 51: Sample of Items Completed This Week
Model Evaluation Summary — Business Goal Alignment
Data Mining Goals Met:
  Predict price using 16 features: RF achieves R²=0.946, MAE=$35.58 (~3.5% error)
  Identify most important features: location_cluster and region are top drivers
  Compare three tree-based models: RF (0.946) > XGB (0.939) > HistGB (0.934)
Feature Importance Consensus (Top 4 per model):
Conclusion: All three models met the accuracy target. Geography is the dominant price driver.
Feature | RF | HistGB | XGB
location_cluster | 1 | 1 | 1
region | 2 | 3 | 2
sqfeet | 3 | 2 | —
lat | 4 | — | —
long | — | 4 | —
baths | — | — | 3
laundry_options | — | — | 4

## Slide 52: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  None at this time

## Slide 53: Next Steps
Task 5.2: Review Process (finalise)
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
Task 5.3: Determine Next Steps (continuing)
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 20 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.1: Plan Deployment
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.2: Plan Monitoring and Maintenance
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A

## Slide 54: Personal Reflection
Phase 5 is progressing well. The model evaluation work confirmed what I suspected from Phase 4, Random Forest is the clear winner, and location-based features dominate the rankings. The process review has been useful for stepping back and looking at the project holistically; I identified a few areas where I could have been more efficient during data preparation. The main push now is wrapping up the Phase 5 report and getting clarity on the Phase 6 tasks, since Professor Nardi confirmed that deployment plans need to be written even without a physical deployment. I feel on track for the July 4 deadline.

## Slide 55: Thank You!...

## Slide 56
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending June 19, 2026 Submitted by Gordon Oboh June 19, 2026

## Slide 57: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 58: Status Overview
Project Status: GREEN
Task 4.2: Generate Test Design
  Status: GREEN — 100% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: 19 Jun 2026
Task 4.3: Build Model
  Status: GREEN — 100% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: 19 Jun 2026
Task 4.4: Assess Model
  Status: GREEN — 100% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: 19 Jun 2026
Task 5.1: Evaluate Results
  Status: GREEN — 5% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
Task 5.2: Review Process
  Status: GREEN — 5% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A

## Slide 59: Items Completed This Week
Task 4.2: Generate Test Design
  Status: GREEN — 100% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: 19 Jun 2026
  80/20 train-test split finalized (113,682 train / 28,421 test rows)
  Evaluation metrics: MAE, MSE, RMSE, R², ASE, SSE, Observed Avg
  Test design documented in Phase 4 report
Task 4.3: Build Model
  Status: GREEN — 100% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: 19 Jun 2026
  All three models trained on 16-feature matrix (113,682 train rows)
  Hyperparameter tuning completed across 6 iterative runs
  Final configs: RF (n_estimators=500), HistGB (max_iter=3000, early_stopping), XGBoost (n_estimators=2000)
  OvP, feature importance, and ASE-vs-trees plots generated for each model
Task 4.4: Assess Model
  Status: GREEN — 100% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: 19 Jun 2026
  Random Forest: R²=0.946 (MAE: $35.58)
  XGBoost: R²=0.939
  HistGradientBoosting: R²=0.934
  Feature importance analyzed across all three models

## Slide 60: Items In Progress
Task 5.1: Evaluate Results
  Status: GREEN — 5% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
  Remaining: compare model metrics, identify best performer, analyze feature importance
Task 5.2: Review Process
  Status: GREEN — 5% complete
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
  Remaining: assess data-mining goals, document gaps and lessons learned

## Slide 61: Items To Be Started
Task 5.3: Determine Next Steps
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
  Decide deploy or revise; document recommended improvements
Task 6.1: Plan Deployment
  Original Start: 5 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 18 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Presentation
  Original Start: 19 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Report
  Original Start: 19 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 62: Sample of Items Completed This Week
Model Performance Comparison
All three models achieved R² above 0.93. Random Forest is best: R²=0.946, MAE=$35.58 (~3.5% error vs $1,016 mean price).
Feature Importance Rankings — Top 4 by Model
Location-based features dominate: location_cluster is #1 across all models. Geographic features account for 4 of 7 ranked slots.
Model | MAE | RMSE | R² | ASE
Random Forest | $35.58 | $77.32 | 0.946 | 5,978.4
HistGradientBoost | $47.07 | $85.70 | 0.934 | 7,344.9
XGBoost | $46.47 | $82.58 | 0.939 | 6,820.1
Feature | RF | HistGB | XGB
location_cluster | 1 | 1 | 1
region | 2 | 3 | 2
sqfeet | 3 | 2 | —
lat | 4 | — | —
long | — | 4 | —
baths | — | — | 3
laundry_options | — | — | 4

## Slide 63: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  Phase 6 scope and schedule
    Awaiting prof. guidance on skipping Tasks 6.1/6.2 (no production deployment) and on handling July 11/18 status reports
    Mitigation: message sent to Prof. Nardi on June 19 requesting clarification

## Slide 64: Next Steps
Task 5.1: Evaluate Results (continuing)
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
Task 5.2: Review Process (continuing)
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: 19 Jun 2026
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
Task 5.3: Determine Next Steps
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Presentation
  Original Start: 19 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 25 Jul 2026 | Revised: N/A | Actual End: N/A
Task 6.3: Final Report
  Original Start: 19 Jul 2026 | Revised: N/A | Actual Start: N/A
  Original End: 1 Aug 2026 | Revised: N/A | Actual End: N/A

## Slide 65: Personal Reflection
Phase 4 wrapped up solidly. Getting all three models trained and evaluated by the June 20 deadline took more iterations than I initially expected, but the results justify the effort. Random Forest landing at R² of 0.946 was a strong outcome. Seeing the feature importance plots confirm that location_cluster, region, and square footage are the dominant price drivers, which aligns with domain knowledge. I am satisfied with the modeling results and feel well positioned heading into Phase 5.

## Slide 66: Thank You!...

## Slide 67
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending June 12, 2026 Submitted by Gordon Oboh June 12, 2026

## Slide 68: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 69: Status Overview
Project Status: GREEN
Task 4.1: Select Modeling Technique
  Status: GREEN — 100% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 6 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: 19 Jun 2026
Task 4.2: Generate Test Design
  Status: GREEN — 50% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.3: Build Model
  Status: GREEN — 40% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.4: Assess Model
  Status: GREEN — 10% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 70: Items Completed This Week
Task 4.1: Select Modeling Technique
  Status: GREEN — 100% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 6 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: 19 Jun 2026
  Three tree-based candidates selected: Random Forest, HistGradientBoostingRegressor, XGBoost
  HistGradientBoostingRegressor chosen over standard GradientBoostingRegressor (56x faster with sample dataset, comparable R-squared)

## Slide 71: Items In Progress
Task 4.2: Generate Test Design
  Status: GREEN — 60% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
  Remaining: finalize split ratios, metric specs, document test design
Task 4.3: Build Model
  Status: GREEN — 40% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
  Remaining: hyperparameter refinement, model comparison write-up, ensemble exploration
Task 4.4: Assess Model
  Status: GREEN — 10% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
  Remaining: full metric collection, residual analysis, feature importance, model comparison

## Slide 72: Items To Be Started
Task 5.1: Evaluate Results
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A
Task 5.2: Review Process
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A

## Slide 73: Sample of Items Completed This Week
Model Training; All Three Models
Random Forest (n_estimators=500), HistGradientBoostingRegressor (max_iter=3000), XGBoost (n_estimators=2000) trained on preprocessed 16-feature matrix (113,682 train rows).
rf = RandomForestRegressor(
n_estimators=500, max_depth=None, min_samples_leaf=1,
max_features="sqrt", random_state=42, n_jobs=-1)
gb = HistGradientBoostingRegressor(max_iter=3000,
learning_rate=0.05, max_depth=7, max_leaf_nodes=63,
min_samples_leaf=1, early_stopping='auto', random_state=42)
xgb = XGBRegressor(
n_estimators=2000, learning_rate=0.05, max_depth=7,
subsample=0.8, colsample_bytree=0.8, random_state=42, n_jobs=-1)

## Slide 74: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  None at this time

## Slide 75: Next Steps
Task 4.2: Generate Test Design (finalize)
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.3: Build Model (continue)
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.4: Assess Model (continue)
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 7 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 5.1: Evaluate Results
  Original Start: 21 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 4 Jul 2026 | Revised: N/A | Actual End: N/A

## Slide 76: Personal Reflection
Phase 4 is off to a strong start. Getting the baseline Random Forest up and running in the first week of Modeling felt productive, though I know the hard part is ahead with hyperparameter tuning and the secondary models. The preprocessed matrices from Phase 3 made the transition smooth — having those 16 features ready to go saved at least a couple of days. I am aiming to have all four modeling tasks substantially complete by the June 20 deadline, with the main question being how much tuning depth is realistic within the remaining time.

## Slide 77: Thank You!...

## Slide 78
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending June 5, 2026 Submitted by Gordon Oboh June 6, 2026

## Slide 79: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 80: Status Overview
Project Status: GREEN
Task 3.3: Construct Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 5 Jun 2026
Task 3.4: Integrate Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 5 Jun 2026
Task 3.5: Format Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 5 Jun 2026

## Slide 81: Items Completed This Week
Task 3.3: Construct Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 5 Jun 2026
  K-Means clustering (k=148) engineered from lat/long; cluster labels converted to strings for target-encoding; train/test split (80/20, random_state=42) before clustering to prevent leakage.
Task 3.4: Integrate Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 5 Jun 2026
  No external data integration required; numeric and categorical feature matrices finalized (11 numeric + 5 categorical including location_cluster).
Task 3.5: Format Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 5 Jun 2026
  TargetEncoder (smoothing=10) applied; final train: 115,284 x 16, test: 28,821 x 16.

## Slide 82: Items In Progress
Task 4.1: Select Modeling Technique
  Status: GREEN — 1% complete
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: 6 Jun 2026
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
  Initial candidates: Random Forest, HistGradientBoostingRegressor, XGBoost (tree-based, scale-invariant).

## Slide 83: Items To Be Started
Task 4.2: Generate Test Design
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.3: Build Model
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.4: Assess Model
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 84: Sample of Items Completed This Week
Geographic and Apartment Filtering — Before/After Comparison
Cleaning narrowed 384,977 listings to ~144K Southern apartments

## Slide 85: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  None at this time

## Slide 86: Next Steps
Task 4.2: Generate Test Design
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.3: Build Model
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.4: Assess Model
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 87: Personal Reflection
Phase 3 wrapped up right on schedule, and honestly it was closer than I would have liked. The target encoding versus one-hot encoding trade-off took more deliberation than expected, and getting the K-Means clustering to align with the 148 Craigslist regions required several iterations. I am relieved all five tasks landed by the June 6 deadline, it was tight but the pipeline is solid. The single Southern bounding box approach ended up simplifying the cleaning logic considerably, which saved time in the final push. Looking ahead to Phase 4, having clean preprocessed matrices ready means we can hit the ground running with modeling next week.

## Slide 88: Thank You!...

## Slide 89
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending May 29, 2026 Submitted by Gordon Oboh May 29, 2026

## Slide 90: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 91: Status Overview
Project Status: GREEN
Task 3.1: Select Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 29 May 2026
Task 3.2: Clean Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 29 May 2026
Task 3.3: Construct Data
  Status: GREEN — 60% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
Task 3.4: Integrate Data
  Status: GREEN — 60% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
Task 3.5: Format Data
  Status: GREEN — 10% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 92: Items Completed This Week
Task 3.1: Select Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 29 May 2026
  Non-predictive columns (id, url, image_url, description) identified and dropped; 18 predictive columns retained for modeling; initial outlier scan flagged 2,236 anomalous price/sqfeet records (0.58%) for cleaning.
Task 3.2: Clean Data
  Status: GREEN — 100% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: 29 May 2026
  Southern states & apartment filter applied: 384,977 to 144,105 records across 17 Southern states.

## Slide 93: Items In Progress
Task 3.3: Construct Data
  Status: GREEN — 60% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
  Train/test split complete (80/20); KMeans location clustering implemented for lat/long coordinates; remaining work includes feature interaction terms and derived variables.
Task 3.4: Integrate Data
  Status: GREEN — 60% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
  Numeric and categorical feature matrices defined; column groups finalized (11 numeric, 5 categorical including location_cluster); final integration tested and working.
Task 3.5: Format Data
  Status: GREEN — 10% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
  Target encoder configured; imputation strategy defined (median for numeric, most_frequent for categorical, Missing category for laundry/parking); final matrices (115,284 train, 28,821 test x 16 features) produced; remaining work on encoding parameter refinement.

## Slide 94: Items To Be Started
Task 4.1: Select Modeling Technique
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 95: Sample of Items Completed This Week
Sample Code — IQR Outlier Removal by Region:
  def clean_outliers(df, TARGET="price", scope="region", k=1.5):
  q1 = df.groupby(scope)[TARGET].transform(
  lambda s: s.quantile(0.25)
  )
  q3 = df.groupby(scope)[TARGET].transform(
  lambda s: s.quantile(0.75)
  )
  iqr = q3 - q1
  mask = (df[TARGET] >= q1 - k*iqr) & (df[TARGET] <= q3 + k*iqr)
  return df[mask].copy()

## Slide 96: Issues, Risks, Concerns
Issues
  Parking options missing rate increased from 36.5% to 51.2% after Southern/apartment filtering.
    Impact: roughly half of Southern apartment listings lack parking data; imputation strategy is more consequential.
    Mitigation: Missing preserved as its own category during target encoding so the model can learn from absence patterns.
Risks
  None at this time
Concerns
  None at this time

## Slide 97: Next Steps
Task 3.3: Construct Data (continuing)
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
Task 3.4: Integrate Data (continuing)
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
Task 3.5: Format Data (continuing)
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: 23 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
Task 4.1: Select Modeling Technique
  Original Start: 7 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 98: Personal Reflection
This was a productive midpoint week for Data Preparation. Having Tasks 3.1 and 3.2 fully wrapped up feels good: especially since I started the phase ahead of schedule. The geographic cleaning and IQR outlier removal were straightforward once I had the logic right, but the Southern states and apartment filters confirmed that our project scope will produce a solid ~144K record dataset to work with. The missing rate jump for parking_options (36% to 51%) after filtering caught my attention, though treating it as its own encoding category should handle it. I am a little surprised that we are already nearing the end of Phase 3 with the midterm presentation coming up: there is still a lot of Phase 4 ahead, but the data pipeline is shaping up well and the early modeling results in the notebook are promising. Confidence remains high.

## Slide 99: Thank You!...

## Slide 100
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending May 22, 2026 Submitted by Gordon Oboh May 22, 2026

## Slide 101: Agenda
Status Overview
Items Completed This Week
Items In Progress
Items To Be Started
Samples of Items Completed This Week
Issues, Risks, Concerns
Next Steps
Personal Reflection

## Slide 102: Status Overview
Project Status: GREEN
Task 2.2: Describing Data
  Status: GREEN — 100% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual: 23 May 2026
Task 2.3: Exploring Data
  Status: GREEN — 100% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual: 23 May 2026
Task 2.4: Verifying Data Quality
  Status: GREEN — 100% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual: 19 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual: 23 May 2026

## Slide 103: Items Completed This Week
Task 2.2: Describing Data
  Status: GREEN — 100% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual: 23 May 2026
  Features classified into numeric (price, sqfeet, beds, baths), categorical binary (amenity flags), categorical multi-class (region, type, laundry_options, parking_options), geographic (lat, long, state), and text/URL (excluded from modeling).
Task 2.3: Exploring Data
  Status: GREEN — 100% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual: 23 May 2026
  Summary statistics computed; apartments most common listing type; Q3 rental price $1,395, Q3 square footage 1,150 sqft; majority pet-friendly; furnished, EV charging, and wheelchair access represent minority listings.
Task 2.4: Verifying Data Quality
  Status: GREEN — 100% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual: 19 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual: 23 May 2026
  Missing value analysis complete: laundry_options 20.5% missing, parking_options 36.5% missing, lat/long 0.5% missing; anomalies identified including $0 price listings and sub-1 sqft listings; all quality issues documented for remediation in Data Preparation phase.

## Slide 104: Items In Progress
Task 3.1: Select Data
  Status: GREEN — 25% complete
  Original Start: 24 May 2026 | Revised: N/A | Actual: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual: N/A
  Started ahead of schedule; initial column selection in progress (dropping non-predictive columns: id, url, image_url, description).

## Slide 105: Items To Be Started
Task 3.2: Clean Data
  Original Start: 24 May 2026 | Revised: N/A | Actual: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual: N/A
Task 3.3: Construct Data
  Original Start: 24 May 2026 | Revised: N/A | Actual: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual: N/A
Task 4.1: Select Modeling Technique
  Original Start: 7 Jun 2026 | Revised: N/A | Actual: N/A
  Original End: 20 Jun 2026 | Revised: N/A | Actual: N/A

## Slide 106: Sample of Items Completed This Week
What: Dataset Acquisition and Exploratory Distributions — Price and Square Footage
  Why: The Kaggle Craigslist dataset (384,977 rows, 558 MB) is the foundation for all subsequent analysis.
Code used to assess data quality:
  def summary_table(df, categorical_cols=None):
  if categorical_cols is None:
  categorical_cols = []
  summary = pd.DataFrame({
  "Column": df.columns,
  "Data Type": df.dtypes.values,
  "Non-Null Count": df.notnull().sum().values,
  "Missing Values": df.isnull().sum().values,
  "Missing %": ((df.isnull().sum() / len(df)) * 100).values
  })
  if categorical_cols is not None:
  summary["Num Categories"] = [
  df[col].nunique(dropna=False) if col in categorical_cols else None
  for col in df.columns
  ]
  return summary
  categorical_cols = ["region","type","cats_allowed", "dogs_allowed",
  "smoking_allowed", "wheelchair_access",
  "electric_vehicle_charge", "comes_furnished",
  "laundry_options", "parking_options", "state"]
  display(summary_table(df, categorical_cols))
  display(df.describe())

## Slide 107: Issues, Risks, Concerns
Issues
  None at this time
Risks
  None at this time
Concerns
  None at this time

## Slide 108: Next Steps
Task 3.1: Select Data (continuing)
  Original Start: 24 May 2026 | Revised: N/A | Actual: 12 May 2026
  Original End: 6 Jun 2026 | Revised: N/A | Actual: N/A
Task 3.2: Clean Data
  Original Start: 24 May 2026 | Revised: N/A | Actual: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual: N/A
Task 3.3: Construct Data
  Original Start: 24 May 2026 | Revised: N/A | Actual: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual: N/A
Task 3.4: Integrate Data
  Original Start: 24 May 2026 | Revised: N/A | Actual: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual: N/A
Task 3.5: Format Data
  Original Start: 24 May 2026 | Revised: N/A | Actual: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual: N/A

## Slide 109: Personal Reflection
The Data Understanding phase went better than expected this week; having all four tasks (2.1 through 2.4) wrapped up on time gave me a real sense of momentum after Task 1.4 running a few days late. What surprised me most was the sheer size of the dataset; nearly 385,000 rows felt overwhelming at first, but once I started working through the distributions and quality checks it became clear there is strong signal in the data. The missing value rates for laundry and parking options (20% and 36%) are higher than I hoped, but finding them now means the Data Preparation phase has a clear plan. I am also slightly ahead of schedule on Task 3.1, which feels good given the midterm presentation is on the horizon. My confidence in the project direction is high.

## Slide 110: Thank You!...

## Slide 111
Housing Amenities Impact on Apartment Listing Prices in the Southern USA
Status Report
Week Ending May 15, 2026
Submitted by Gordon Oboh May 15, 2026

## Slide 112: Agenda…
Status Overview…
Items Completed in Current Week…
Items In Progress…
Items To Be Started…
Samples of Items Completed This Week…
Issues, Risks, Concerns…
Next Steps…
Personal Reflection…

## Slide 113: Status Overview
Project Status is GREEN
Task 1.4: Produce Project Plan
  Task is GREEN — 100% complete
  Original Start: 2 May 2026 | Revised: N/A | Actual Start: 7 May 2026
  Original End: 9 May 2026 | Revised: N/A | Actual End: 13 May 2026
  Completed 4 days after original end date
Task 2.1: Gathering Data
  Task is GREEN — 100% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual Start: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual End: 23 May 2026
Task 2.2: Describing Data
  Task is GREEN — 75% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual Start: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual End: 23 May 2026
Task 2.3: Exploring Data
  Task is GREEN — 50% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual Start: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual End: 23 May 2026
Task 2.4: Verifying Data Quality
  Task is GREEN — 0% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual Start: N/A
  Original End: 23 May 2026 | Revised: N/A | Actual End: N/A

## Slide 114: Items Completed in Current Week
Task 1.4: Produce Project Plan
  Task is GREEN — 100% complete
  Original Start: 2 May 2026 | Revised: N/A | Actual Start: 7 May 2026
  Original End: 9 May 2026 | Revised: N/A | Actual End: 13 May 2026
  Full CRISP-DM project timeline built out with task dates, deliverables, and resource plan
  Completed 4 days after original end; delay due to scope of timeline build-out
Task 2.1: Gathering Data
  Task is GREEN — 100% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual Start: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual End: 23 May 2026
  Dataset sourced from Kaggle: Craigslist housing listings scraped January 2020; 384,977 rows, 22 columns, 558.44 MB

## Slide 115: Items In Progress
Task 2.2: Describing Data
  Task is GREEN — 75% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual Start: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual End: N/A
  Features classified: numeric (price, sqfeet, beds, baths), categorical binary (amenity flags), multi-class (region, type, laundry, parking), geographic (lat, long, state), text/URL excluded
Task 2.3: Exploring Data
  Task is GREEN — 50% complete
  Original Start: 11 May 2026 | Revised: N/A | Actual Start: 12 May 2026
  Original End: 23 May 2026 | Revised: N/A | Actual End: N/A
  Summary statistics computed; Q3 price $1,395, Q3 sqft 1,150; majority pet-friendly; ~25% smoke-friendly

## Slide 116: Items To Be Started
Task 2.4: Verifying Data Quality
  Original Start: 11 May 2026 | Revised: N/A | Actual Start: N/A
  Original End: 23 May 2026 | Revised: N/A | Actual End: N/A
Task 3.1: Select Data
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 117: Sample of Items Completed This Week
Dataset Acquisition and Exploratory Distributions
  Price and Square Footage
Data Source: Kaggle — Craigslist Housing Listings (Jan 2020)
  384,977 rows x 22 columns, 558.44 MB | Target: price (monthly USD)
Price Distribution (Southern States):
  Right-skewed; majority below $3,000/month; median near $1,100; long upper tail with outliers above $10,000 flagged for removal
Square Footage Distribution (Southern States):
  Right-skewed; Q3 = 1,150 sqft; extreme outliers flagged as anomalies; IQR-based removal planned per state/region
Why shown:
  The Kaggle dataset is the foundation for all analysis. Confirming successful acquisition and understanding price/sqft distributions validates that Data Understanding produced a usable dataset.

## Slide 118: Project Issues, Risks, Concerns
Issues
  Missing value concentration: laundry_options (20.5%) and parking_options (36.5%) have substantial missing rates
    Impact: imputation strategy will influence model results for two key amenity features
    Mitigation: evaluating between removing or encoding them differently
Risks
  None at this time
Concerns
  None at this time

## Slide 119: Next Steps
Task 3: Data Preparation
  Original Start: 24 May 2026 | Revised: N/A | Actual Start: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 120: Personal Reflection
The Data Understanding phase went better than expected this week; having Task 2.1 (Gathering Data) wrapped up on time gave me momentum after Task 1.4 running a few days late. What surprised me most was the sheer size of the dataset; nearly 385,000 rows felt overwhelming at first, but once I started working through the distributions and quality checks I realized there is a lot of useful information to work with. There is still a lot left to do, but I am making consistent progress.

## Slide 121: Thank You!...

## Slide 122
Housing Amenities Impact on Apartment Listing Prices in the Southern USA Status Report Week Ending May 09, 2026 Submitted by Gordon Oboh May 09, 2026

## Slide 123: Agenda…
Status Overview…
Items Completed in Current Week…
Items In Progress…
Items To Be Started…
Samples of Items Completed This Week…
Issues, Risks, Concerns…
Next Steps…
Personal Reflection…

## Slide 124: Status Overview…
Project Status is GREEN
DS Project Proposal Revision (Tasks 1.1–1.3)
  Task is GREEN — content complete, PDF deliverable pending
  Original Start: 2 May 2026 | Revised Start: N/A | Actual Start: 2 May 2026
  Original End: 9 May 2026 | Revised End: N/A | Actual End: N/A
  Professor approved: "Gordon...housing amenities it is!...Mr. N."
Task 1.4: Produce a Project Plan
  Task is GREEN — in progress
  Original Start: 2 May 2026 | Revised Start: N/A | Actual Start: 7 May 2026
  Original End: 9 May 2026 | Revised End: N/A | Actual End: N/A

## Slide 125: Items Completed in Current Week…
DS Project Proposal Revision
  Task is GREEN — content complete, PDF deliverable pending
  Original Start: 2 May 2026 | Revised Start: N/A | Actual Start: 2 May 2026
  Original End: 9 May 2026 | Revised End: N/A | Actual End: N/A
  PDF documentation not yet started
Task 1.1: Determine Business Objectives — Deliverable: Project Scope Document Part 1
  Task is GREEN — complete
  Original Start: 2 May 2026 | Revised Start: N/A | Actual Start: 2 May 2026
  Original End: 9 May 2026 | Revised End: N/A | Actual End: 7 May 2026
  Business objectives defined: analyze amenity impact on Southern USA apartment rental pricing
Task 1.2: Assess the Situation — Deliverable: Project Scope Document Part 2
  Task is GREEN — complete
  Original Start: 2 May 2026 | Revised Start: N/A | Actual Start: 2 May 2026
  Original End: 9 May 2026 | Revised End: N/A | Actual End: 7 May 2026
  Data sources identified; geographic scope set to 6 Southern cities
Task 1.3: Determine Data-Mining Goals — Deliverable: Data-Mining Scope Document
  Task is GREEN — complete
  Original Start: 2 May 2026 | Revised Start: N/A | Actual Start: 2 May 2026
  Original End: 9 May 2026 | Revised End: N/A | Actual End: 7 May 2026
  Data-mining goal: identify amenity features with strongest predictive power on rental price

## Slide 126: Items In Progress…
Task 1.4: Produce a Project Plan — Deliverable: Data Mining Project/Resource Plan
  Task is GREEN — in progress
  Original Start: 2 May 2026 | Revised Start: N/A | Actual Start: 7 May 2026
  Original End: 9 May 2026 | Revised End: N/A | Actual End: N/A
  Plan requires full CRISP-DM timeline build-out

## Slide 127: Items to Be Started…
Task 2.1: Gathering Data — Deliverable: Data Collection Report
  Original Start: 12 May 2026 | Revised Start: N/A | Actual Start: N/A
  Original End: 23 May 2026 | Revised End: N/A | Actual End: N/A
  No schedule change; data sources being evaluated
Task 2.2: Describing Data — Deliverable: Data Description Report
  Original Start: 23 May 2026 | Revised Start: N/A | Actual Start: N/A
  Original End: 30 May 2026 | Revised End: N/A | Actual End: N/A

## Slide 128: Sample of Items Completed This Week…
Project Proposal — Phase 1 (Phase_1.tex)
  Defines project scope; received professor approval — foundation for all CRISP-DM phases
  Project 1: Housing Amenities Impact on Apartment Listing Prices in the Southern USA
  Real estate investors and property managers in the Southern USA lack quantitative evidence on which amenities drive rental pricing. This project analyzes apartment listings to determine which amenities most significantly influence rental prices.

## Slide 129: Project Issues, Risks, Concerns…
Issues
  None at this time
Risks
  Geographic scope initially too broad
    Impact: analysis would lack regional specificity, reducing actionability
    Mitigation: narrowed focus to 6 Southern cities per professor feedback
Concerns
  Identifying suitable data sources for Southern USA apartment listings
    Impact: inability to find quality data could delay or limit analysis scope
    Mitigation: actively evaluating available options before data collection phase begins

## Slide 130: Next Steps…
Task 1.4: Produce Project Plan (continuing)
  Original Start: 2 May 2026 | Revised: N/A | Actual Start: 7 May 2026
  Original End: 9 May 2026 | Revised: N/A | Actual End: N/A
Task 2.1: Gathering Data — Deliverable: Data Collection Report
  Original Start: 12 May 2026 | Revised: N/A | Actual Start: N/A
  Original End: 23 May 2026 | Revised: N/A | Actual End: N/A
Task 2.2: Describing Data — Deliverable: Data Description Report
  Original Start: 23 May 2026 | Revised: N/A | Actual Start: N/A
  Original End: 30 May 2026 | Revised: N/A | Actual End: N/A
Task 2.3: Exploring Data — Deliverable: Data Exploration Report
  Original Start: 30 May 2026 | Revised: N/A | Actual Start: N/A
  Original End: 6 Jun 2026 | Revised: N/A | Actual End: N/A
Task 2.4: Verifying Data Quality
  Original Start: 6 Jun 2026 | Revised: N/A | Actual Start: N/A
  Original End: 13 Jun 2026 | Revised: N/A | Actual End: N/A

## Slide 131: Personal Reflection…

## Slide 132: Thank You!...