## Slide 1: CS 703 Applied Data Science Project Weekly Status Report
Professor Nicholas Nardi
Spring 2026

## Slide 2
Predictive Pricing Analysis for The USA Housing Market Status Report Week Ending May 9, 2026 Submitted by Gordon Oboh May 10, 2026

## Slide 3: Agenda…
Status Overview…
Items Completed in Current Week…
Items In Progress…
Items To Be Started…
Samples of Items Completed This Week…
Issues, Risks, Concerns…
Next Steps…
Personal Reflection…

## Slide 4: Status Overview…
Project Status is Yellow
  1.0 Business Understanding — in progress; business problem identified
  Original Start: May 4, 2026 | Revised Start: N/A | Actual Start: May 4, 2026
  Original End: May 9, 2026 | Revised End: N/A | Actual End: N/A
    Dataset search ongoing; suitable rental listing data not yet confirmed
  Phase 1: Project Proposals — completed
  Original Start: May 4, 2026 | Revised Start: N/A | Actual Start: May 4, 2026
  Original End: May 9, 2026 | Revised End: N/A | Actual End: May 9, 2026
  No other major issues

## Slide 5: Items Completed in Current Week…
Phase 1: Project Proposals Document
  Task is GREEN — 100% complete
  Original Start: May 4, 2026 | Revised Start: N/A | Actual Start: May 4, 2026
  Original End: May 9, 2026 | Revised End: N/A | Actual End: May 9, 2026
  Documented two candidate data science projects; primary focus confirmed as housing amenity impact on U.S. rental pricing
    Submitted to Professor Nardi for review

## Slide 6: Items In Progress…
1.0 Business Understanding
  Task is Yellow — 75% complete
  Original Start: May 4, 2026 | Revised Start: N/A | Actual Start: May 4, 2026
  Original End: May 9, 2026 | Revised End: N/A | Actual End: N/A
    Business problem and scope are defined; awaiting dataset confirmation
    Anticipate completing 1.0 Business Understanding once data source is secured

## Slide 7: Items to Be Started…
1.1 Determine Business Objectives (subsection of current 1.0)
  Original Start: May 10, 2026 | Revised Start: N/A | Actual Start: N/A
  Original End: May 11, 2026 | Revised End: N/A | Actual End: N/A
1.2 Assess Situation
  Original Start: May 11, 2026 | Revised Start: N/A | Actual Start: N/A
  Original End: May 12, 2026 | Revised End: N/A | Actual End: N/A
2.0 Data Understanding (next CRISP-DM phase)
  Original Start: May 13, 2026 | Revised Start: N/A | Actual Start: N/A
  Original End: May 24, 2026 | Revised End: N/A | Actual End: N/A

## Slide 8: Sample of Items Completed This Week…
CRISP-DM Methodology — Project Framework
  The diagram below shows the CRISP-DM process model guiding this project.
    Phase 1.0 Business Understanding is the current active phase.

## Slide 9: Project Issues, Risks, Concerns…
Issues
  None at this time
Risks
  Dataset availability: a suitable publicly accessible rental listing dataset may not exist
    Impact: project scope or direction may need revision
    Mitigation: evaluating Kaggle, UCI, and government housing data repositories
Concerns
  None at this time

## Slide 10: Next Steps…
Complete 1.0 Business Understanding
  Original Start: May 4, 2026 | Revised: N/A | Actual Start: May 4, 2026
  Original End: May 9, 2026 | Revised: N/A | Actual End: N/A
1.1 Determine Business Objectives
  Original Start: May 10, 2026 | Revised: N/A | Actual Start: N/A
  Original End: May 11, 2026 | Revised: N/A | Actual End: N/A
1.2 Assess Situation
  Original Start: May 11, 2026 | Revised: N/A | Actual Start: N/A
  Original End: May 12, 2026 | Revised: N/A | Actual End: N/A
Begin 2.0 Data Understanding
  Original Start: May 13, 2026 | Revised: N/A | Actual Start: N/A
  Original End: May 24, 2026 | Revised: N/A | Actual End: N/A

## Slide 11: Personal Reflection…
Week 1 has been a grounding experience. Defining the business problem forced me to think beyond just "what can I model" and toward "what question actually matters." That shift in framing took more effort than expected, but it feels like the right foundation.
The main thing on my mind is the data. I know the direction I want to go, but without a confirmed dataset, everything else is provisional. I am cautiously optimistic but aware that this uncertainty needs to resolve early before it affects the rest of the project.

## Slide 12: Thank You!...